Your logo goes here: save as public/branding/qis-logo.png and re-run — we’ll drop it in automatically.

ACCESS CONTROL MODERNIZATION

Proposal for CEVA Logistics

Pro-Watch decommission + Avigilon ACM / Mercury — two Mount Juliet facilities, priced honestly.

US-MJB-04 + US-MJB-02 • Planning investment (both sites): $472,747.30

Quality Installation Systems

2 Robert Browning
Knoxville, TN 37932
865-774-4444  •  Robert@qualityinstallationsystems.com

Prepared for: CEVA Logistics
Proposal date: May 12, 2026
Valid 15 calendar days through May 27, 2026.

OCIP (quick read): Owner-Controlled Insurance Program — sometimes the owner sponsors wrap coverage; sometimes there’s a small contractor fee. We show a conservative allowance you can zero out once CEVA confirms the program.

# Executive snapshot

The one-minute version.

This isn’t “swap badges and disappear.” It’s a controlled decommission of legacy Pro-Watch, a disciplined Mercury + Avigilon ACM installation, cable and pathway work that respects CEVA’s standards (yes—including the 500 ft homerun rule), and a closeout package you can actually hand to IT and Security without wincing.

## At a glance — planning totals

| Site | Scope (headline) | Planning total |
| --- | --- | --- |
| US-MJB-04 G&R Warehouse | 12014 Volunteer Blvd, Mount Juliet, TN | $194,985.97 |
| US-MJB-02 CL Warehouse (Building 3) | 12008 Volunteer Blvd, Building 3, Mount Juliet, TN | $277,761.33 |
| Program | Both sites (sum of planning totals above) | $472,747.30 |

## Why Quality Installation Systems

We translate RFP language into **staffable hours** and a **BOM you can defend**—not a single mystery lump sum.

Rough-in, headend landing, programming, SAT, and **documentation** are split so procurement sees where the money goes.

Exclusions are explicit (gates/intercoms/Cisco packages unless in your SOW)—fewer “surprise” scopes after award.

We’ve already thought about **long buildings**: if drawings push past the 500 ft rule, we talk **IDF / aux** early—not after cable is on the truck.

How to read the rest of this document: Each site has its own BOM (with cable + lift logic), labor buildup, and financial summary. Assumptions and exclusions follow—because boring fine print is what keeps projects out of court.
P.S. If you want this deck even sharper, send a vector PDF title block next time—phone photos of D-size sheets are heroic, but they don’t do your scale bar any favors.

# Assumptions & exclusions

The fine print that keeps everyone friends.

Labor hours are planning estimates based on CEVA-provided quantities plus a five-reader buffer per site; engineered drawings may adjust scope via change order.

Loaded labor rate: $155.00/hr.

PM / supervision: 12% of **direct labor dollars** (hours × rate), then contractor margin 25% applies to (direct labor + PM).

Material pricing shown is an **indicative market-cost BOM** (internet/distributor-style placeholders) **before** 25% contractor margin; replace with formal distributor quotes.

Sales & use tax shown at 9.25% on **material sell** only (placeholder — verify taxable treatment and local rate).

Performance/payment bond allowance: 1.50% of pre-tax construction subtotal (labor sell + material sell) — verify with your surety.

OCIP / wrap allowance: 0.50% of pre-tax construction subtotal — **zero this** if CEVA confirms owner-provided wrap with no contractor contribution.

Intercoms, vehicle gates, turnstiles, Cisco licensing/SFP/fiber, and wireless bridges are excluded unless listed in a site-specific SOW attachment.

RFP completion milestone referenced in discussions: June 25, 2026 — confirm current contract schedule.

Cable takeoff uses CEVA **500 ft maximum** reader/controller homerun rule: each opening must be ≤500 ft to its panel (or IDF/aux panel). Until a survey exists, we price **parallel homeruns** using a planning **average path length** per reader, plus **10 ft** field service loop per homerun and **10%** spool/waste allowance. Any run over 500 ft requires an **IDF/aux** (extra panel, rack ports, fiber/media) — **change order**.

Lift / aerial equipment: BOM includes a **rental-day allowance** (all-in placeholder). Operator labor for lift moves is generally embedded in field labor hours; fuel/damage waiver may be extra per rental contract.

# US-MJB-04 — site package

Scope + numbers for this facility.

G&R Warehouse
12014 Volunteer Blvd, Mount Juliet, TN
Planning quantities: 19 reader openings (CEVA +5 buffer), 7 LP1502 positions.

## Bill of materials (indicative market pricing) — US-MJB-04

Quantities and unit costs are **planning placeholders** until distributor quotes and engineered drawings are issued.

| Item | Qty | Unit (est.) | Extended (est.) | Notes |
| --- | --- | --- | --- | --- |
| HID Multi-Class Signo 40 / 40K readers (blend — IT keypads as required) | 19 | $485.00 | $9,215.00 |  |
| Mercury LP1502 controller | 7 | $1,750.00 | $12,250.00 |  |
| Mercury MR52-S3 I/O module (typical mix per panel) | 10 | $395.00 | $3,950.00 |  |
| LifeSafety Power / LSP-style enclosure & distribution (per cluster) | 7 | $2,050.00 | $14,350.00 |  |
| REX motion (DS150i/DS160 class — model per RFI) | 14 | $88.00 | $1,232.00 |  |
| Door contacts (interior/exterior mix) | 12 | $42.00 | $504.00 |  |
| Sounder/strobe (IN/OUT & alarmed door allowance) | 6 | $240.00 | $1,440.00 |  |
| Electric strike / EL / door hardware allowance (non-locksmith) | 10 | $175.00 | $1,750.00 |  |
| Cat6 plenum green + patch / Cyber SSPS allowance (job lot) | 1 | $1,600.00 | $1,600.00 |  |
| Batteries, power accessories, misc panel consumables (job lot) | 1 | $1,850.00 | $1,850.00 |  |
| Conduit, J-hooks, labels, wire management (job lot) | 1 | $1,100.00 | $1,100.00 |  |
| Decommission supplies, packaging, dumpster/recycle allowance | 1 | $800.00 | $800.00 |  |
| Freight / logistics allowance | 1 | $850.00 | $850.00 |  |
| Yellow plenum composite — reader homeruns (est. 19 runs × (300+10) ft × (1+10%) waste) | 6479 | $1.22 | $7,904.38 | planning; each run ≤500 ft to panel/IDF per CEVA; survey to confirm |
| Yellow plenum 22/6 SHLD — IN/OUT homeruns (est. 6 runs × (280+10) ft × (1+10%) waste) | 1914 | $2.95 | $5,646.30 | planning; each run ≤500 ft to panel/IDF per CEVA; survey to confirm |
| Cable misc. (ties, transition, spare box, label stock for pulls) | 1 | $450.00 | $450.00 |  |
| Aerial / scissor lift rental (est. 6 days, all-in incl. delivery/pickup allowance) | 6 | $245.00 | $1,470.00 | Verify Sunbelt/United/etc. quote; operator training/OSHA site rules apply |
| Material base (pre-margin) | — | — | $66,361.68 | Sum of BOM |

## Labor buildup

| Phase / scope bucket | Hours | Rate ($155.00/hr) | Extended |
| --- | --- | --- | --- |
| A — Pre-mobilization (setup, coordination, prerequisites) | 20 | $155.00 | $3,100.00 |
| B — Pro-Watch decommission (remove, cable, inventory, light patch) | 76 | $155.00 | $11,780.00 |
| C — Rough-in (pathway, homeruns, service loops, headend rough-in) | 96 | $155.00 | $14,880.00 |
| D — Headend install (LSP / LP1502 / MR52 landing & checkout) | 70 | $155.00 | $10,850.00 |
| E — Device install (readers, terminations, door interfaces — spread est.) | 70 | $155.00 | $10,850.00 |
| F — Power-on checks & comms troubleshooting | 18 | $155.00 | $2,790.00 |
| G — ACM programming (hardware map, doors, schedules per contract) | 50 | $155.00 | $7,750.00 |
| H — Commissioning / SAT & punch | 24 | $155.00 | $3,720.00 |
| I — Closeout documentation (as-builts, panel schedules, turnover) | 40 | $155.00 | $6,200.00 |
| Direct labor subtotal | 464 | — | $71,920.00 |
| PM / supervision (12% of direct labor $) | — | — | $8,630.40 |
| Subtotal before contractor margin (direct + PM) | — | — | $80,550.40 |
| Contractor margin on labor services (25%) | — | — | $20,137.60 |
| Labor sell total | — | — | $100,688.00 |

## Financial summary — US-MJB-04

| Category | Amount (USD) |
| --- | --- |
| Labor sell total (incl. PM & margin) | $100,688.00 |
| Material base (BOM, pre-margin) | $66,361.68 |
| Contractor margin on materials (25%) | $16,590.42 |
| Material sell total | $82,952.10 |
| Pre-tax construction subtotal (labor sell + material sell) | $183,640.10 |
| Est. sales/use tax on materials (9.25% — verify) | $7,673.07 |
| Performance & payment bond allowance (1.50% of pre-tax subtotal — verify) | $2,754.60 |
| OCIP / wrap allowance (0.50% of pre-tax subtotal — verify or zero) | $918.20 |
| TOTAL (this site) | $194,985.97 |

# US-MJB-02 — site package

Scope + numbers for this facility.

CL Warehouse (Building 3)
12008 Volunteer Blvd, Building 3, Mount Juliet, TN
Planning quantities: 27 reader openings (CEVA +5 buffer), 11 LP1502 positions.

## Bill of materials (indicative market pricing) — US-MJB-02

Quantities and unit costs are **planning placeholders** until distributor quotes and engineered drawings are issued.

| Item | Qty | Unit (est.) | Extended (est.) | Notes |
| --- | --- | --- | --- | --- |
| HID Multi-Class Signo 40 / 40K readers (blend — IT keypads as required) | 27 | $485.00 | $13,095.00 |  |
| Mercury LP1502 controller | 11 | $1,750.00 | $19,250.00 |  |
| Mercury MR52-S3 I/O module (typical mix per panel) | 14 | $395.00 | $5,530.00 |  |
| LifeSafety Power / LSP-style enclosure & distribution (per cluster) | 11 | $2,050.00 | $22,550.00 |  |
| REX motion (DS150i/DS160 class — model per RFI) | 20 | $88.00 | $1,760.00 |  |
| Door contacts (interior/exterior mix) | 16 | $42.00 | $672.00 |  |
| Sounder/strobe (IN/OUT & alarmed door allowance) | 10 | $240.00 | $2,400.00 |  |
| Electric strike / EL / door hardware allowance (non-locksmith) | 14 | $175.00 | $2,450.00 |  |
| Cat6 plenum green + patch / Cyber SSPS allowance (job lot) | 1 | $2,400.00 | $2,400.00 |  |
| Batteries, power accessories, misc panel consumables (job lot) | 1 | $2,650.00 | $2,650.00 |  |
| Conduit, J-hooks, labels, wire management (job lot) | 1 | $1,550.00 | $1,550.00 |  |
| Decommission supplies, packaging, dumpster/recycle allowance | 1 | $950.00 | $950.00 |  |
| Freight / logistics allowance | 1 | $1,100.00 | $1,100.00 |  |
| Yellow plenum composite — reader homeruns (est. 27 runs × (340+10) ft × (1+10%) waste) | 10395 | $1.22 | $12,681.90 | planning; each run ≤500 ft to panel/IDF per CEVA; survey to confirm |
| Yellow plenum 22/6 SHLD — IN/OUT homeruns (est. 8 runs × (300+10) ft × (1+10%) waste) | 2728 | $2.95 | $8,047.60 | planning; each run ≤500 ft to panel/IDF per CEVA; survey to confirm |
| Cable misc. (ties, transition, spare box, label stock for pulls) | 1 | $650.00 | $650.00 |  |
| Aerial / scissor lift rental (est. 9 days, all-in incl. delivery/pickup allowance) | 9 | $245.00 | $2,205.00 | Verify Sunbelt/United/etc. quote; operator training/OSHA site rules apply |
| Material base (pre-margin) | — | — | $99,941.50 | Sum of BOM |

## Labor buildup

| Phase / scope bucket | Hours | Rate ($155.00/hr) | Extended |
| --- | --- | --- | --- |
| A — Pre-mobilization | 25 | $155.00 | $3,875.00 |
| B — Pro-Watch decommission | 100 | $155.00 | $15,500.00 |
| C — Rough-in | 138 | $155.00 | $21,390.00 |
| D — Headend install | 98 | $155.00 | $15,190.00 |
| E — Device install | 96 | $155.00 | $14,880.00 |
| F — Power-on checks | 24 | $155.00 | $3,720.00 |
| G — ACM programming | 64 | $155.00 | $9,920.00 |
| H — Commissioning / SAT & punch | 32 | $155.00 | $4,960.00 |
| I — Closeout documentation | 50 | $155.00 | $7,750.00 |
| Direct labor subtotal | 627 | — | $97,185.00 |
| PM / supervision (12% of direct labor $) | — | — | $11,662.20 |
| Subtotal before contractor margin (direct + PM) | — | — | $108,847.20 |
| Contractor margin on labor services (25%) | — | — | $27,211.80 |
| Labor sell total | — | — | $136,059.00 |

## Financial summary — US-MJB-02

| Category | Amount (USD) |
| --- | --- |
| Labor sell total (incl. PM & margin) | $136,059.00 |
| Material base (BOM, pre-margin) | $99,941.50 |
| Contractor margin on materials (25%) | $24,985.38 |
| Material sell total | $124,926.88 |
| Pre-tax construction subtotal (labor sell + material sell) | $260,985.88 |
| Est. sales/use tax on materials (9.25% — verify) | $11,555.74 |
| Performance & payment bond allowance (1.50% of pre-tax subtotal — verify) | $3,914.79 |
| OCIP / wrap allowance (0.50% of pre-tax subtotal — verify or zero) | $1,304.93 |
| TOTAL (this site) | $277,761.33 |

# Program roll-up (both sites)

One number for the conference call.

| Line | Amount (USD) |
| --- | --- |
| US-MJB-04 — total (per site table) | $194,985.97 |
| US-MJB-02 — total (per site table) | $277,761.33 |
| — | — |
| Recomputed pre-tax subtotal (labor + material, both sites) | $444,625.97 |
| Combined est. tax on materials (same method) | $19,228.81 |
| Combined bond allowance (on combined pre-tax) | $6,669.39 |
| Combined OCIP allowance (on combined pre-tax) | $2,223.13 |
| GRAND TOTAL (both sites, recomputed) | $472,747.30 |

Pick one story and stick to it: either **sum of per-site totals** or the **recombined grand** above (they should be close; recombined applies bond/OCIP once on the combined pre-tax base).

## Let’s build it right

We’re ready to align on drawings, IDF strategy, and cutover windows the moment CEVA says “go.” Questions welcome — we actually answer the phone.

Respectfully submitted,

Robert Browning
Authorized Signer
Quality Installation Systems