OPTION / ADD-ON ESTIMATES

Not included in base access control bid
CEVA Logistics — priced separately per site

Quality Installation Systems • 865-774-4444 • Robert@qualityinstallationsystems.com
2 Robert Browning, Knoxville, TN 37932
Schedule of options • May 12, 2026

Purpose: Separate optional packages (PKG-A Intercoms, PKG-B Vehicle gates, PKG-C Turnstiles/ADA, PKG-D Network/Cisco/fiber augmentation) were discussed as potential scope outside the base reader/panel/decommission estimates. Each site follows on its own page.

# US-MJB-04 — addon packages (exclude from base bid)

G&R Warehouse
12014 Volunteer Blvd, Mount Juliet, TN

These packages were excluded from the base access control modernization bid unless explicitly listed in your site-specific SOW. Hours are planning bands; midpoints drive sell pricing below. Labor methodology matches base proposal: loaded $155.00/hr direct, 12% PM on direct labor dollars, 25% contractor margin on labor subtotal.

| Code | Addon | Hrs (low–mid–high) | Mid labor sell ⓘ | Material (plan) | Key assumption |
| --- | --- | --- | --- | --- | --- |
| PKG-B | Vehicle gates package (dual-height pedestals / readers) | 80 / 120 / 175 | $26,040.00 | Pedestals, readers, keypad-upper/reader-lower, cable, conduit (excluded vendor hardware per RFP clarification). Quote separate. | Planning basis: truck gate pedestal count from walk-through (4 pedestal faces); inbound+outbound vehicle lanes per CEVA program (Wright-style); excludes gate operators, loops, barriers, civil (per typical CEVA language). Underground-rated cable pulls + terminations + interface testing. |
| PKG-C | Full-height turnstile + ADA gate (Alvarado-class integration) | 28 / 48 / 72 | $10,416.00 | Turnstile / ADA equipment by others or GC package often — ACS integration labor + minor materials only unless BOM states otherwise. | Planning basis: 1 turnstile + 1 ADA path from site notes; inbound/outbound readers, crash-bar on ADA, DPS, sounders if IN/OUT policy applies — confirm on drawings. |
| PKG-A | Intercom subsystem (Axis / 2N substations + answering stations + ACC) | 72 / 105 / 145 | $22,785.00 | Intercom hardware, mounts, UPS at masters — distributor BOM; excludes ACC server licensing/storage beyond scope. | Planning basis: dual-height gate package often drives 8 substation-mount points + 4 desk masters (program call-all-masters); Green Cat6 homeruns + composite spare pairs for triggers; ACC video-channel setup. Adjust counts when SOW finalized. |
| PKG-D | Network augmentation (Cisco / Meraki optics / fiber jumpers / hardened edge — when in ACS vendor scope) | 6 / 18 / 36 | $3,906.00 | LIC-C9300 / IE / SFP SKUs — non-returnable; price after exact switch qty confirmed. OM3 LC jumpers qty TBD. | Planning labor: documenting serial #s for portal, patching, fiber jumper install at rack, coordination with Network Support only if awarded to QIS. Often IT-owned — treat as optional. |
| TOTAL (midpoint hrs) | Σ packages | 291 hrs (mid components only) | $63,147.00 | Mid labor sells summed row-by-row (PM/margin embedded per line). | Material: quote distributor per final SOW. |

ⓘ Mid labor sell = (155.0/hr × mid hours) + 12% PM + 25% margin chain. Low/high hours scale roughly proportionally — PM/margin recomputed linearly.

# US-MJB-02 — addon packages (exclude from base bid)

CL Warehouse (Building 3)
12008 Volunteer Blvd, Building 3, Mount Juliet, TN

These packages were excluded from the base access control modernization bid unless explicitly listed in your site-specific SOW. Hours are planning bands; midpoints drive sell pricing below. Labor methodology matches base proposal: loaded $155.00/hr direct, 12% PM on direct labor dollars, 25% contractor margin on labor subtotal.

| Code | Addon | Hrs (low–mid–high) | Mid labor sell ⓘ | Material (plan) | Key assumption |
| --- | --- | --- | --- | --- | --- |
| PKG-B | Vehicle gates package (dual-height pedestals / readers) | 90 / 135 / 200 | $29,295.00 | Same exclusions: gate operators/hardware excluded pending RFP carve-out confirmation. | Same gate methodology as sibling site; MJB-02 notes include 4 truck gate pedestals and heavier dock/ramp footprint — labor midpoint slightly higher than MJB-04. |
| PKG-C | Full-height turnstile + ADA gate integration | 28 / 48 / 72 | $10,416.00 | Equipment sourcing same as Site 01. | Planning basis: 1 turnstile + ADA from walk-through notes. |
| PKG-A | Intercom subsystem (Axis / 2N + ACC video channels) | 85 / 125 / 170 | $27,125.00 | Hardware BOM TBD — confirm substation count per finalized gate plan. | Slightly denser dock/gate clustering in notes — midpoint hours + programming higher than Site 01 until drawing-based count. |
| PKG-D | Network augmentation (optics / documentation / rack fiber) | 10 / 22 / 45 | $4,774.00 | Pass-through SKUs — verify quantities with Network Support before order. | Optional if scope includes switch-port physical work beyond yellow Cat6 to demarc. |
| TOTAL (midpoint hrs) | Σ packages | 330 hrs (mid components only) | $71,610.00 | Mid labor sells summed row-by-row (PM/margin embedded per line). | Material: quote distributor per final SOW. |

ⓘ Mid labor sell = (155.0/hr × mid hours) + 12% PM + 25% margin chain. Low/high hours scale roughly proportionally — PM/margin recomputed linearly.

# Program summary — both sites (midpoint)

| Site | Mid planning hours (all addons) | Mid labor sell (sum of lines) |
| --- | --- | --- |
| US-MJB-04 | 291 | $63,147.00 |
| US-MJB-02 | 330 | $71,610.00 |
| BOTH — reference only | 621 | $134,757.00 |

Material for gate hardware, turnstiles, intercom SKU packs, Cisco licenses/SFP/fiber assemblies is intentionally not rolled up until CEVA confirms option scope and issues a vendor BOM or PO-directed SKUs.

## Disclaimer

Indicative planning hours only until gate lane counts, intercom substation quantities, Turnstile model sheets, and Cisco port maps are finalized. Selecting any option triggers a distributor material quote and coordinated SAT plan.