OPTION / ADD-ON ESTIMATES

Not included in base access control bid
CEVA Logistics — US-LUI-02 (Louisville KY) — priced separately

Quality Installation Systems • 865-774-4444 • Robert@qualityinstallationsystems.com
2 Robert Browning, Knoxville, TN 37932
Schedule of options • May 12, 2026

Purpose: PKG-A Intercoms, PKG-B Vehicle gates, PKG-C Turnstiles/ADA, PKG-D Network/Cisco augmentation — optional scope outside the base reader/panel / Pro-Watch decommission estimate for this facility only.

# US-LUI-02 — addon packages (exclude from base bid)

CL Warehouse
5200 Interchange Drive, Louisville, KY 40229

These packages were excluded from the base access control modernization bid unless explicitly listed in your site-specific SOW. Hours are planning bands; midpoints drive sell pricing below. Labor methodology matches base proposal: loaded $155.00/hr direct, 12% PM on direct labor dollars, 25% contractor margin on labor subtotal.

| Code | Addon | Hrs (low–mid–high) | Mid labor sell ⓘ | Material (plan) | Key assumption |
| --- | --- | --- | --- | --- | --- |
| PKG-B | Vehicle gates package (dual-height pedestals / readers) | 78 / 115 / 168 | $24,955.00 | Pedestals, readers, keypad/reader stacks, conduit — quote distributor once lane plan is sealed. Operators excluded pending RFP. | Planning basis: 5200 Interchange CL warehouse — verify truck lane count and pedestal layout on drawings; typical dual-height pedestal program (inbound/outbound lanes) aligns with sibling CEVA sites until site walk adjusts counts. Excludes gate operators, loops, barriers, civil. Underground-rated pulls + terminations + interface testing. |
| PKG-C | Full-height turnstile + ADA gate (Alvarado-class integration) | 28 / 48 / 72 | $10,416.00 | Turnstile / ADA equipment frequently GC or OEM package — ACS integration labor + minor materials unless BOM states otherwise. | Planning basis: 1 turnstile + 1 ADA path assumed until egress sheets confirm; inbound/outbound readers, crash-bar on ADA (DPS / sounders if IN/OUT policy applies). |
| PKG-A | Intercom subsystem (Axis / 2N substations + answering stations + ACC) | 65 / 98 / 138 | $21,266.00 | Intercom hardware / UPS — distributor BOM; excludes ACC licensing/storage beyond negotiated SOW. | Planning basis: Louisville gate/dock clustering — midpoint slightly below larger Mount Juliet footprints; adjust substation counts when finalized along PKG-B perimeter. Green Cat6 homeruns + composite spares for triggers; ACC channel setup scope as awarded. |
| PKG-D | Network augmentation (Cisco / Meraki optics / fiber jumpers / hardened edge — when in ACS vendor scope) | 6 / 16 / 34 | $3,472.00 | 9300-class LIC / IE / OM3 LC jumpers — confirm switch map with Network Support before order. | Planning labor: patching, jumper install, serialization for portal optics — **only if** IT awards physical layer to QIS. Often IT-owned scope. |
| TOTAL (midpoint hrs) | Σ packages | 277 hrs (mid components only) | $60,109.00 | Mid labor sells summed row-by-row (PM/margin embedded per line). | Material: quote distributor per final SOW. |

ⓘ Mid labor sell = (155.0/hr × mid hours) + 12% PM + 25% margin chain. Low/high hours scale roughly proportionally — PM/margin recomputed linearly.

## Disclaimer

Indicative planning hours until gate lanes, intercom substation quantities, turnstile sheets, and Cisco port maps are finalized. Selecting any option triggers distributor material quoting and SAT coordination.